## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 30 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21
|  |  |  | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04
|  |  | 120 | 114 | 108 | 102 | 96 | 90 | 84 | 78 | 72 | 66 | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0 | 0 | Ideal Burndown
|  |  | 120 | 112 | 104 | 96 | 90 | 87 | 83 | 80 | 73 | 64 | 55 | 48 | 43 | 41 | 40 | 30 | 23 | 18 | 12 | 7 | 0 | 0 | Remaining Hrs (Total)
Creating Game classes | Desing Main menu screen | Rohit Sharma | 16 | 14 | 12 | 10 | 8 | 7 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| implement command pattern in menu screen | Rachit Chokshi | 16 | 15 | 14 | 13 | 13 | 13 | 11 | 11 | 10 | 9 | 7 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design Menu module classes | Srivatsa | 16 | 14 | 12 | 10 | 8 | 7 | 7 | 6 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design Help screen | Tarun Arora | 16 | 14 | 12 | 10 | 8 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0
| Design player module | Rachit Chokshi | 16 | 15 | 14 | 13 | 13 | 13 | 12 | 11 | 10 | 8 | 6 | 4 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Integrating Game classes | Integrating different game modules | Srivatsa | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integrating different game modules | Tarun Arora | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integrating different game modules | Rohit Sharma | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
| Integrating different game modules | Rachit Chokshi | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing the end to end functionalities and code refactoring | Testing and deploying the game | Srivatsa | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 0 | 0
| Testing and deploying the game | Rohit Sharma | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 0 | 0
| Testing and deploying the game | Rachit Chokshi | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0
| Testing and deploying the game | Tarun Arora | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0
Team:
Rohit Sharma | 10 hours / Week
Rachit Chokshi | 10 hours / Week
Tarun Arora | 10 hours / Week
Srivatsa Mulpuri | 10 hours / Week
Total Available Hours During Sprint: | 120